# Execution Roadmap: ER Minoxidil Development to Human Use

# Execution Roadmap

## From Formulation to Human Use

Date: February 5, 2026

Product: Extended-Release Minoxidil 8.5 mg (Lipid Matrix)

### Overview: 5 Phases Before Human Use

| Phase | Duration | Cost Estimate | Gate |
| --- | --- | --- | --- |
| 1. Formulation Development | 2-4 weeks | $2-5K | Dissolution meets spec |
| 2. Analytical & QC | 2-3 weeks | $3-8K | Methods validated |
| 3. Stability Testing | 1-6 months (parallel) | $2-5K | No degradation at 1 month |
| 4. Animal PK (Optional) | 4-6 weeks | $30-50K | PK profile acceptable |
| 5. Compounding Setup | 2-4 weeks | $1-3K | Pharmacy ready to compound |
| TOTAL (without animal PK) | 6-10 weeks | $8-21K |  |
| TOTAL (with animal PK) | 10-14 weeks | $38-71K |  |

## Phase 1: Formulation Development

Duration: 2-4 weeks | Cost: $2,000-5,000

### 1.1 Make Test Batches

- Source excipients (Compritol, Precirol, PEG 6000, Poloxamer 188, MCC, lactose)

- Source minoxidil API (USP grade)

- Make 3 small batches (50-100 units each) per the formulation protocol

- Document batch records for each

- Visual inspection: tablets/capsules uniform, no defects

### 1.2 Dissolution Testing (Critical)

- Run dissolution on each batch (1, 4, 8, 12 hours)

- Compare to target: 15-20% (1h), 40-50% (4h), 65-75% (8h), >80% (12h)

- If too fast: increase Compritol, decrease PEG

- If too slow: decrease Compritol, increase PEG

- Iterate until dissolution meets target (may need 2-4 iterations)

### 1.3 Fed-State Dissolution

- Run dissolution in FeSSIF or milk (simulates fed state)

- Compare to fasted state dissolution

- Acceptable if fed-state 4h dissolution is <1.5x fasted

- If food effect too high: add calcium stearate or carnauba wax

Phase 1 Exit Criteria:

- Dissolution meets target profile in fasted media

- Food effect is acceptable (<1.5x at 4h)

- Batch-to-batch variability <15%

## Phase 2: Analytical & Quality Control

Duration: 2-3 weeks | Cost: $3,000-8,000

### 2.1 Assay Method

- HPLC method for minoxidil content (or use compendial USP method)

- Verify method works with your matrix (lipid interference check)

- Run assay on 3 batches: target 95-105% of label claim

### 2.2 Content Uniformity

- Test 10 individual units from each batch

- Calculate AV (Acceptance Value) per USP <905>

- Target: AV ≤ 15.0

### 2.3 Physical Tests

- Weight variation (±5%)

- Hardness (tablets): 6-10 kP

- Friability (tablets): <1.0%

- Disintegration: should NOT disintegrate in <1 hour (it's ER)

Phase 2 Exit Criteria:

- Assay: 95-105% of label claim

- Content uniformity: AV ≤ 15.0

- Physical tests pass

## Phase 3: Stability Testing

Duration: Ongoing (1-6 months) | Cost: $2,000-5,000

### 3.1 Accelerated Stability

- Place samples at 40°C / 75% RH

- Test at: 1 week, 2 weeks, 1 month, 3 months, 6 months

- Test: Appearance, Assay, Dissolution, DSC (lipid form)

### 3.2 Real-Time Stability

- Place samples at 25°C / 60% RH

- Test at: 1 month, 3 months, 6 months, 12 months

- This runs in parallel - don't wait for completion

### 3.3 DSC/XRD Monitoring (Polymorphism)

- Run DSC at T0 and each stability timepoint

- Watch for peak shifts indicating polymorphic transition

- If dissolution slows >15% at 1 month accelerated: investigate

Minimum Before Human Use:

- 1-month accelerated stability data with no significant changes

- Dissolution within ±10% of initial

- No assay drop >5%

You can proceed to human use after 1-month accelerated data while continuing longer stability studies.

## Phase 4: Animal PK Study (Recommended but Optional)

Duration: 4-6 weeks | Cost: $30,000-50,000

### 4.1 Study Design

- Species: Beagle dogs (n=6)

- Design: 3-way crossover (ER fasted, ER fed, IR solution)

- Dose: ~2-3 mg/kg (approximately 20-30 mg per dog)

- Washout: 1 week between periods

### 4.2 Sampling & Analysis

- Blood samples: pre-dose, 0.5, 1, 2, 3, 4, 6, 8, 12, 24h

- Plasma separation and storage at -80°C

- LC-MS/MS analysis for minoxidil

- Calculate: Cmax, Tmax, AUC0-24, food effect ratio

### 4.3 Success Criteria

- Tmax delayed ≥2 hours vs IR

- Cmax reduced ≥25% vs IR

- AUC ≥70% of IR (bioavailability acceptable)

- Food effect <2-fold on Cmax

When to Skip Animal PK:

- If going compounding-only route (503A)

- If dissolution data looks excellent

- If budget is limited - can do human PK directly (with physician oversight)

Animal PK de-risks but isn't strictly required for compounding.

## Phase 5: Compounding Setup

Duration: 2-4 weeks | Cost: $1,000-3,000

### 5.1 Pharmacy Selection

- Identify 2-3 candidate compounding pharmacies

- Confirm lipid matrix / melt granulation capability

- Confirm 503A or 503B registration

- Request references / quality certifications

- Select pharmacy partner

### 5.2 Technology Transfer

- Provide formulation protocol to pharmacy

- Review process with their pharmacist

- Pharmacy makes qualification batch

- Run dissolution on pharmacy's batch

- Confirm results match your development batches

### 5.3 Prescriber Setup

- Identify 1-3 dermatologists willing to prescribe off-label

- Provide them with: formulation info, dosing rationale, safety data

- Establish prescription workflow with pharmacy

- Create patient consent/information document

Phase 5 Exit Criteria:

- Pharmacy can successfully compound the formulation

- Pharmacy's batch matches your dissolution profile

- At least one prescribing physician ready

- Patient information materials ready

## Dissolution Testing Providers

### Budget Options (Fast & Cheap)

#### 1. University Pharmaceutical Sciences Labs

Cost: $50-150 per dissolution run

Turnaround: 1-2 weeks

Pros: Cheapest option; may provide consulting

Cons: Slower; may have scheduling constraints

How to find: Contact pharmacy schools with dissolution equipment (most do)

Examples:

- University of Michigan College of Pharmacy

- University of Texas at Austin College of Pharmacy

- University of North Carolina Eshelman School of Pharmacy

- Rutgers Ernest Mario School of Pharmacy

- Any local pharmacy school with equipment access

#### 2. PCCA (Professional Compounding Centers of America)

Cost: $200-500 per dissolution profile

Turnaround: 1-2 weeks

Pros: Compounding-focused; understands your application

Cons: May prioritize member pharmacies

Contact: pccarx.com | 800-331-2498

#### 3. Contract Testing Labs (Mid-Range)

Cost: $300-800 per dissolution profile

Turnaround: 5-10 business days

| Lab | Location | Website |
| --- | --- | --- |
| Analytical Food Laboratories (AFL) | Grand Prairie, TX | afltexas.com |
| Intertek Pharmaceutical Services | Multiple locations | intertek.com |
| Element Materials Technology | Multiple locations | element.com |
| SGS Life Sciences | Multiple locations | sgs.com |
| Eurofins Lancaster Labs | Lancaster, PA | eurofins.com |

### Full-Service CROs (More Expensive but Comprehensive)

#### 4. Specialty Pharma CROs

Cost: $1,000-3,000 per study

Turnaround: 2-4 weeks

Pros: Full service; can do dissolution + assay + stability

| CRO | Specialty | Website |
| --- | --- | --- |
| Absorption Systems (Pharmaron) | Dissolution, PK | absorption.com |
| Gateway Analytical | Physical characterization | gatewayanalytical.com |
| Particle Sciences (Lubrizol) | Formulation support | particlesciences.com |
| Metrics Contract Services | Full CMC package | metricscontractservices.com |
| Catalent | Full service CDMO | catalent.com |

### DIY Option

#### 5. Buy/Rent Equipment

Cost: $5,000-15,000 (used dissolution apparatus) or $500-1,000/month rental

Pros: Unlimited testing; fast iteration

Cons: Need HPLC/UV for analysis; space requirements

Equipment sources:

- eBay / LabX (used equipment)

- Agilent, Sotax, Distek (new equipment)

- Excedr (equipment leasing)

### Recommended Approach

Start with a university lab or PCCA for initial dissolution testing ($50-200/run). If you need more than 5-10 runs, consider a contract lab for efficiency.

Budget estimate for dissolution testing:

- Development phase (10-15 runs): $500-2,000

- Fed-state testing (3-5 runs): $150-500

- Stability testing (10-15 runs over 6 months): $500-1,500

- Total: $1,150-4,000

## Animal PK Study Providers

If you decide to do the dog PK study:

| CRO | Location | Estimated Cost | Notes |
| --- | --- | --- | --- |
| Absorption Systems (Pharmaron) | Exton, PA | $35-50K | Excellent for oral PK; IVIVC expertise |
| QPS Holdings | Newark, DE | $30-45K | Good for small studies |
| Covance (Labcorp Drug Development) | Madison, WI | $40-60K | Large CRO; may have minimums |
| Charles River | Multiple | $40-55K | Large CRO; comprehensive |
| ICON (PRA Health Sciences) | Multiple | $35-50K | Good for crossover designs |
| Frontage Laboratories | Exton, PA | $25-40K | Often more competitive pricing |

## Master Checklist: Before Human Use

### CRITICAL REQUIREMENTS

- Dissolution meets target profile (20-25% 1h, 50-60% 4h, >85% 12h)

- Assay: 95-105% of label claim

- Content uniformity: AV ≤ 15.0

- 1-month accelerated stability: no significant change

- Compounding pharmacy can reproduce your results

- Licensed physician willing to prescribe

- Patient information/consent document prepared

### Complete Pre-Human Checklist

| # | Task | Status | Required? |
| --- | --- | --- | --- |
| 1 | Finalize formula composition | ☐ | Yes |
| 2 | Source all excipients (pharma grade) | ☐ | Yes |
| 3 | Source minoxidil API (USP grade, with COA) | ☐ | Yes |
| 4 | Make development batches (3 minimum) | ☐ | Yes |
| 5 | Dissolution testing - fasted media | ☐ | Yes |
| 6 | Dissolution testing - fed state media | ☐ | Yes |
| 7 | Iterate formula if dissolution off-spec | ☐ | If needed |
| 8 | Assay testing (HPLC) | ☐ | Yes |
| 9 | Content uniformity testing | ☐ | Yes |
| 10 | Physical testing (weight, hardness, friability) | ☐ | Yes |
| 11 | Place samples on accelerated stability | ☐ | Yes |
| 12 | 1-month accelerated stability results | ☐ | Yes |
| 13 | DSC testing for polymorphism | ☐ | Recommended |
| 14 | Dog PK study (fed/fasted) | ☐ | Optional (recommended) |
| 15 | Identify compounding pharmacy partner | ☐ | Yes |
| 16 | Technology transfer to pharmacy | ☐ | Yes |
| 17 | Pharmacy qualification batch | ☐ | Yes |
| 18 | Dissolution on pharmacy's batch | ☐ | Yes |
| 19 | Identify prescribing physician(s) | ☐ | Yes |
| 20 | Create patient information document | ☐ | Yes |
| 21 | Establish prescription workflow | ☐ | Yes |
| 22 | Document all development work | ☐ | Yes |

## Recommended Sequence

WEEK 1-2: Source materials, make first batches
    │
    ▼
WEEK 2-3: Dissolution testing (iterate if needed)
    │
    ▼
WEEK 3-4: QC testing (assay, CU, physical)
    │
    ├──────────────────────────────────┐
    ▼                                  ▼
WEEK 4+: Stability testing         WEEK 4-5: Pharmacy outreach
(runs in parallel)                     │
    │                                  ▼
    │                              WEEK 5-6: Tech transfer
    │                                  │
    ▼                                  ▼
WEEK 8: 1-month stability          WEEK 6-7: Pharmacy qualification
         results                       │
    │                                  ▼
    └──────────────┬───────────────────┘
                   │
                   ▼
            WEEK 8-10: Ready for first patient
                   │
                   ▼
            OPTIONAL: Dog PK study (parallel track, 4-6 weeks)

## Budget Summary

| Item | Low Estimate | High Estimate |
| --- | --- | --- |
| Excipients & API (development quantities) | $500 | $1,500 |
| Dissolution testing (15-20 runs) | $1,000 | $4,000 |
| Assay & CU testing | $500 | $2,000 |
| Physical testing | $200 | $500 |
| Stability testing (6 months) | $1,500 | $4,000 |
| DSC/XRD testing | $300 | $1,000 |
| Pharmacy tech transfer | $500 | $2,000 |
| Contingency (20%) | $900 | $3,000 |
| TOTAL (without dog PK) | $5,400 | $18,000 |
| Dog PK study (optional) | $25,000 | $50,000 |
| TOTAL (with dog PK) | $30,400 | $68,000 |

## Key Decision Points

#### Decision 1: After Initial Dissolution Testing

- If dissolution meets spec: Proceed to QC and stability

- If dissolution too fast: Increase Compritol, decrease PEG, re-test

- If dissolution too slow: Decrease Compritol, increase PEG, re-test

- If can't get it right after 4 iterations: Consider pivoting to MUPS

#### Decision 2: After 1-Month Accelerated Stability

- If stable: Proceed to compounding setup

- If dissolution slows >15%: Add annealing step, re-test

- If assay drops >5%: Investigate degradation, may need formulation change

#### Decision 3: Dog PK Study?

- Do it if: You plan to eventually seek FDA approval, or want to de-risk

- Skip it if: Budget limited, going compounding-only, dissolution looks excellent

Document prepared: February 5, 2026